## Sheet3_(2)
CS 192 Software Engineering II
Implementation Plan and Accountability Report

Developer's Group Name:		SYD
Project Name:		BillDing!

Sprint No.	Date	Activity	Accountability (Name of Person)	Output	Done (Y/N)	Remarks
1	1/25/2017	Plan and prepare Sprint Review Checklist	Anthony Cornell M. Dacoco	Implementation	Y
	1/25-29/2017	Code [XML File for Add View, Reminders View]	Paul Matthew L. Sason	Source Code	N
	1/25-29/2017	Code [Backend for reminder database reading to reminder objects]	Anthony Cornell M. Dacoco	Source Code	N
	1/25-29/2017	Code [Backend for reminder database adding from add view]	Arthur N. Yiu	Source Code	N
	1/30-2/1/2017	Code [Integration of backends to XML]	Paul Matthew L. Sason	Source Code	N
	1/30-2/1/2017	Test [Backend for reminder database reading to reminder objects]	Arthur N. Yiu	Test Scorecard Result	N	Use Test Scorecard done in CS 191
	1/30-2/1/2017	Test [Backend for reminder database adding from add view]	Paul Matthew L. Sason	Test Scorecard Result	N	Use Test Scorecard done in CS 191
	2/1-2/2017	Test [XML File for Add View, Reminder View with Integration]	Anthony Cornell M. Dacoco	Test Scorecard Result	N	Use Test Scorecard done in CS 191
	2/2/2017	Code Review [Backend for reminder database reading to reminder objects]	Arthur N. Yiu	Code Review Result	N
	2/2/2017	Code Review [Backend for reminder database adding from add view]	Paul Matthew L. Sason	Code Review Result	N
	2/2/2017	Code Review [XML File for Add View, Reminder View with Integration]	Anthony Cornell M. Dacoco	Code Review Result	N
	1/25-29/2017	Others [Study Android Studio and Java]	Arthur N. Yiu		N
	1/25-29/2017	Others [Study Android Studio and Java]	Paul Matthew L. Sason		N
	1/25-29/2017	Others [Study Android Studio and Java]	Anthony Cornell M. Dacoco		N
	2/2/2017	Sprint Review	Arthur N. Yiu	Sprint Review Document	N	<App Name> - Sprint1Review.odt
	2/2/2017	Sprint Retrospect	Paul Matthew L. Sason	Sprint Retrospect Document	N	Link to Sprint Release codes in GitHub
2	2/6/2017	Plan and prepare Sprint Review Checklist	Anthony Cornell M. Dacoco	Implementation Plan	Y
	2/6-10/2017	Code [Implementation for Notification each Reminder]	Arthur N. Yiu	Source Code	N
	2/10/2017	Code [Modulization of current codes]	Anthony Cornell M. Dacoco	Source Code	N
	2/11/2017	Test [Implementation of Notification]	Paul Matthew L. Sason	Test Scorecard Result	N	Use Test Scorecard done in CS 191
	2/11/2017	Test [Modulization of codes]	Paul Matthew L. Sason	Test Scorecard Result	N	Use Test Scorecard done in CS 191
	2/11/2017	Code Review [Implementation of Notification]	Paul Matthew L. Sason	Code Review Result	N
	2/11/2017	Code Review [Modulization of codes]	Paul Matthew L. Sason	Code Review Result	N
	2/2/2017	Sprint Review	Arthur N. Yiu	Sprint Review Document	N	<App Name> - Sprint2Review.odt
	2/2/2017	Sprint Retrospect	Anthony Cornell M. Dacoco	Sprint Retrospect Document	N	Link to Sprint Release codes in GitHub