## Version_Control
Bills Reminder
Requirements Traceability Matrix

Submitted to:	Ma. Rowena C. Solamo
	Faculty Member
	Department of Computer Science
	College of Engineering
	University of the Philippines, Diliman

Submitted by:	Dacoco, Anthony Cornell M.
	Sason, Paul Matthew L.
	Yiu, Arthur Kevin N.

In partial fulfillment of Academic Requirements
for the course
CS 191 Software Engineering
1st Sem AY 2016-2017

History Revision:

Revision Date	Person Responsible	Version Number	Modification
09/30/2016	Arthur Yui	1.0	Initial Draft
	Paul

## Requirements
RTM ID	Use Case No.	Description	Scenario No	Scenario Description	Priority Status	Has Prototype?
UC-1.0-S1	Use Case 1.0	The system should be able to allow the user to select the option to add a reminder.	S1	Select Add Reminder	Must Have	yes
UC-1.0-S2		The system should be able to allow the user to select the option to update a reminder.	S2	Select Update Reminder	Must Have	yes
UC-1.0-S3		The system should be able to allow the user to select the option to delete a reminder.	S3	Select Delete Reminder	Must Have	yes
UC-1.1-S1	Use Case 1.1	The system should be able to allow the user to add a bill reminder	S1	Add Reminder given complete data	Must Have	yes
UC-1.1-S2		The system should be able to detect and handle events where some required information was not given.	S2	Add Reminder given incomplete data	Must Have	yes
UC-1.1-S3		The system should be able to allow the user to return to the main menu when the user decides to not add a new reminder.	S3	Cancel add reminder.	Must Have	yes
UC-1.2-S1	Use Case 1.2	The system should be able to allow the user to update a bill reminder.	S1	Update reminder given complete data	Must Have	yes
UC-1.2-S2		The system should be able to detect and handle events where some required information was not given.	S2	Update reminder given incomplete data	Must Have	yes
UC-1.2-S3		The system should be able to allow the user to return to the main menu before choosing a reminder to edit.	S3	Cancels before selecting a reminder to update	Must Have	yes
UC-1.2-S4		The system should be able to allow the user to return to the main menu after choosing a reminder to edit.	S4	Cancels after selecting a reminder to update	Must Have	yes
UC-1.3-S1	Use Case 1.3	The system should be able to allow the user to delete a bill reminder.	S1	Delete bill reminder	Must Have	yes
UC-1.3-S2		The system should be able to not delete a reminder when the user does not confirm the deletion.	S2	Cancels delete action on confirmation	Must Have	yes
UC-1.3-S3		The system should be able to allow the user to return to the main menu before choosing a reminder to delete.	S3	Cancels before selecting a reminder to delete	Must Have	yes
UC-1.3-S4		The system should be able to allow the user to return to the main menu after choosing a reminder to delete.	S4	Cancels after selecting a reminder to delete	Must Have	yes
UC-2.0-S1	Use Case 2.0	The system should be able to allow the user to view all of the existing reminders.	S1	Has reminders to display	Must Have	yes
UC-2.0-S2		The system should be able to tell the the user that there are currently no reminders.	S2	No reminders to display	Must Have	yes
UC-3.0-S1	Use Case 3.0	The system should be able to allow the user to modify the reminder settings.	S1	Successfully change settings.	Must Have	yes
UC-3.0-S2		The system should be able to allow the user to return to the main menu when the user decides to not make any changes to the settings.	S2	No changes to the settings.	Must Have	yes

## Sprint_Schedule
Use Case	Description	Story Points	Value Points	BFTB
Use Case 1.0	Add Reminder	21	34	1.619047619
Use Case 4.0	The system should be able to allow the user to view all of the existing reminders.	5	21	4.2
Use Case 6.0	Notify user thru alarm	55	144	2.618181818
Use Case 3.0	Delete Reminder	3	5	1.666666667
Use Case 2.0	Edit Reminder	13	13	1
Use Case 2.1	Tag Reminder as Paid	8	8	1
Use Case 5.0	The system should be able to allow the user to modify the reminder settings.	34	1	0.029411765

	Sort the results by _______	3			could have

		Velocity
Sprint 1	Add Reminder	26
	View Reminders
Sprint 2	Alarm Notification	55
Sprint 3	Delete Reminder	24
	Edit Reminder
	Tag Reminder as Paid
Sprint 4	Reminder Setting Modification	34
Sprint 5	Integration	NaN

## Sheet3
CS 192 Software Engineering II
Implementation Plan and Accountability Report

Developer's Group Name:		SYD
Project Name:		BillDing!

Sprint No.	Date	Activity	Accountability (Name of Person)	Output	Done (Y/N)	Remarks
1	1/25/2017	Plan and prepare Sprint Review Checklist	Anthony Cornell M. Dacoco	Implementation	Y
	1/25-29/2017	Code [XML File for Add View, Reminders View]	Paul Matthew L. Sason	Source Code	N
	1/25-29/2017	Code [Backend for reminder database reading to reminder objects]	Anthony Cornell M. Dacoco	Source Code	N
	1/25-29/2017	Code [Backend for reminder database adding from add view]	Arthur N. Yiu	Source Code	N
	1/30-2/1/2017	Code [Integration of backends to XML]	Paul Matthew L. Sason	Source Code	N
	1/30-2/1/2017	Test [Backend for reminder database reading to reminder objects]	Arthur N. Yiu	Test Scorecard Result	N	Use Test Scorecard done in CS 191
	1/30-2/1/2017	Test [Backend for reminder database adding from add view]	Paul Matthew L. Sason	Test Scorecard Result	N	Use Test Scorecard done in CS 191
	2/1-2/2017	Test [XML File for Add View, Reminder View with Integration]	Anthony Cornell M. Dacoco	Test Scorecard Result	N	Use Test Scorecard done in CS 191
	2/2/2017	Code Review [Backend for reminder database reading to reminder objects]	Arthur N. Yiu	Code Review Result	N
	2/2/2017	Code Review [Backend for reminder database adding from add view]	Paul Matthew L. Sason	Code Review Result	N
	2/2/2017	Code Review [XML File for Add View, Reminder View with Integration]	Anthony Cornell M. Dacoco	Code Review Result	N
	1/25-29/2017	Others [Study Android Studio and Java]	Arthur N. Yiu		N
	1/25-29/2017	Others [Study Android Studio and Java]	Paul Matthew L. Sason		N
	1/25-29/2017	Others [Study Android Studio and Java]	Anthony Cornell M. Dacoco		N
	2/2/2017	Sprint Review	Arthur N. Yiu	Sprint Review Document	N	<App Name> - Sprint1Review.odt
	2/2/2017	Sprint Retrospect	Paul Matthew L. Sason	Sprint Retrospect Document	N	Link to Sprint Release codes in GitHub
2	2/6/2017	Plan and prepare Sprint Review Checklist	Anthony Cornell M. Dacoco	Implementation Plan	Y
	2/6-10/2017	Code [Implementation for Notification each Reminder]	Arthur N. Yiu	Source Code	N
	2/10/2017	Code [Modulization of current codes]	Anthony Cornell M. Dacoco	Source Code	N
	2/11/2017	Test [Implementation of Notification]	Paul Matthew L. Sason	Test Scorecard Result	N	Use Test Scorecard done in CS 191
	2/11/2017	Test [Modulization of codes]	Paul Matthew L. Sason	Test Scorecard Result	N	Use Test Scorecard done in CS 191
	2/11/2017	Code Review [Implementation of Notification]	Paul Matthew L. Sason	Code Review Result	N
	2/11/2017	Code Review [Modulization of codes]	Paul Matthew L. Sason	Code Review Result	N
	2/2/2017	Sprint Review	Arthur N. Yiu	Sprint Review Document	N	<App Name> - Sprint2Review.odt
	2/2/2017	Sprint Retrospect	Anthony Cornell M. Dacoco	Sprint Retrospect Document	N	Link to Sprint Release codes in GitHub